## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | (Fill your Project Number here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
PROJECT NUMBER | 61
PROJECT NAME | Exam Time Table Generator
PROJECT MENTOR (sponsor) | Lalitha/Sriranjani
TEAM MEMBERS | Ahana Talukdar
Ananya Kasavajhala
Himani Das
Keerthana Korlapati
Raghav Grover
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Client meeting | Coordination | Ahana | 0.75 | 0.75 | Done |  | 0 | 0
Create Client Meeting MoM | Documentation | Ananya | 1.5 | 2 | Done |  | -0.5 | 25
Research existing technology | Preparation | Raghav | 2 | 1.5 | Done |  | 0.5 | 33.3333
Requirements Doc | Documentation | Himani | 2.5 | 3 | Done |  | -0.5 | 16.6667
Project Plan writeup | Documentation | Keerthana | 1.5 | 2 | Done |  | -0.5 | 25
Project Concept writeup | Documentation | Ahana | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Ahana | 0.5 | 0.5 | Done |  | 0 | 0
Status tracker | Documentation | Raghav | 1 | 1 | Done |  | 0 | 0
Week 2 (January 22 - January 28)
Team Meeting | Coordination | Ahana | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Raghav | 1 | 1 | Done |  | 0 | 0
Canva Design | Design | Himani, Ananya | 2 | 2 | Done |  | 0 | 0
Client Meeting | Coordination | Ahana | 0.75 | 0.75 | Done |  | 0 | 0
Client Meeting MoM | Documentation | Himani | 0.75 | 1 | Done
Project Plan writeup | Documentation | Keerthana | 2.5 | 2 | Done
Week 3 (January 29 - February 4)
Team Meeting | Coordination | Ahana | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client Meeting | Coordination |  |  |  | Delayed | Did not happen because of Quiz.
Frontend design | Development | Ananya, Himani | 6 | 5 | Done |  | 1 | 20
Algorithm design | Development | Ahana, Keerthana, Raghav | 4 | 5 | Done |  | -1 | 20
Update Requirements Document | Documentation | Ahana | 0.5 | 0.5 | Done |  | 0 | 0
Status tracker | Documentation | Raghav | 1 | 0.75 | Done |  | 0.25 | 33.3333
Week 4 (February 5 - February 11)
Team Meeting | Coordination | Keerthana | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client Meeting | Coordination | Raghav | 0.5 | 0.6 | Done |  | -0.1 | 16.6667
Client Meeting MoM | Documentation | Himani | 1 | 1 | Done |  | 0 | 0
Frontend | Development | Ananya | 12 | 11 | Done |  | 1 | 9.0909
Backend | Development | Ahana | 4 | 4 | Done |  | 0 | 0
Reproduce existing implementation | Development | Raghav | 4 | 3 | Done | To help with the backend algorithm | 1 | 33.3333
Update Requirements Document | Documentation | Keerthana | 1 | 1 | Done
Status Tracker | Documentation | Raghav | 1 | 1 | Done |  | 0 | 0
Week 5 (February 12 - February 18)
Team Meeting | Coordination | Ahana, Himani | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client Meeting | Coordination |  |  |  | Delayed | Client not available
Client Meeting MoM | Documentation |  |  |  | Delayed
SRS Document | Documentation | Ahana, Himani | 4 | 3.5 | Done |  | 0.5 | 14.2857
Analyzing, working on API's | Preparation | Ahana, Keerthana |  |  | Delayed | Not provided by client till now
Frontend | Development | Ananya | 4 | 3.5 | Done |  | 0.5 | 14.2857
Backend algo | Preparation | Raghav, Keerthana | 2.5 | 2 | Done |  | 0.5 | 25
Status Tracker | Documentation | Raghav | 1 | 0.5 | Done |  | 0.5 | 100
Week 6 (February 19 - February 25)
Team Meeting | Coordination | Ananya, Himani | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Ahana, Keerthana | 0.5 | 0.5 | Done | Waiting for approval from client regarding UI | 0 | 0
Client Meeting MoM | Documentation | Keerthana | 1 | 0.75 | Done | List of queries forwarded to the client, waiting for confirmation from Acad office | 0.25 | 33.3333
Integrated the sample data API into algo | Development | Ahana | 2 | 2 | Done | API received | 0 | 0
Frontend | Development | Ananya | 4 | 3.25 | Done |  | 0.75 | 23.0769
Backend algo | Development | Raghav | 4 | 3 | Done |  | 1 | 33.3333
Client-server Integration | Development | Keerthana, Himani | 4 |  | Delayed | Waiting for approval from client regarding UI
Status Tracker | Documentation | Raghav | 0.5 | 0.5 | Done |  | 0 | 0
Week 7 (26 Feb - 4th March)
Team Meeting | Coordination | Himani | 1.5 | 1 | Done |  | 0.5 | 50
Client Meeting | Coordination | Ahana, Keerthana | 1 | 0.5 | Done | Postponed to 5th | 0.5 | 100
Client Meeting MoM | Documentation | Ahana, Raghav | 1.5 | 1 | Done |  | 0.5 | 50
Algo changes | Development | Raghav | 5.5 | 4 | Done |  | 1.5 | 37.5
Frontend | Development | Ananya, Keerthana | 5 | 4 | Done |  | 1 | 25
Status Tracker | Documentation | Raghav | 1 | 0.5 | Done |  | 0.5 | 100
Changed the weekly schedule to follow the grading dates as per TA's instruction
Week 8 (3rd March - 9th March)
Team Meeting | Coordination | Himani | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Ahana | 0.5 | 1 | Done |  | -0.5 | 50
Client Meeting MoM | Documentation | Ahana | 1 | 1 | Done |  | 0 | 0
Frontend | Development | Ananya | 4 | 5 | Done |  | -1 | 20
Backend | Development | Keerthana | 4 | 5.5 | Done |  | -1.5 | 27.2727
Seating arrangement algorithm | Development | Raghav | 4 | 5.25 | Done |  | -1.25 | 23.8095
Design Doc | Documentation | Ahana, Himani | 2 |  | Done
Filtering Previous year data | Preparation | Himani | 1 | 1.5 | Done |  | -0.5 | 33.3333
Status Tracker | Documentation | Raghav | 0.5 | 0.5 | Done |  | 0 | 0
Week 9 (10th March - 16th March)
Team Meeting | Coordination | Himani, Ananya | 1 | 1.25 | Done |  | -0.25 | 20
Client Meeting | Coordination | Ahana, Keerthana | 0.5 | 0.5 | Done |  | 0 | 0
Client Meeting MoM | Documentation | Himani, Ananya | 1 | 1 | Done |  | 0 | 0
Design Doc | Documentation | Ahana, Himani | 3 | 3.5 | Done |  | -0.5 | 14.2857
Frontend Backend Integration | Development | Ananya, Keerthana | 3 | 2 | Done
R1 Presentation | Documentation | Ahana | 3 | 2.5 | Done |  | 0.5 | 20
Code documentation | Documentation | Ahana | 1 | 1 | Done
R1 Final code + Error fixes | Development | Raghav | 8 | 10 | Done |  | -2 | 20
Testing script | Testing | Ahana | 1 | 0.75 | Done
Status Tracker | Documentation | Raghav | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
Week 10 (17th March - 23rd March)
Team Meeting | Coordination | Himani | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Ananya | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client Meeting MoM | Documentation | Himani | 0.5 | 0.5 | Done |  | 0 | 0
R1 Presentation | Documentation | Ahana, Raghav | 2 | 2.5 | Done |  | -0.5 | 20
R1 Demo | Documentation | Raghav | 1 | 0.5 | Done |  | 0.5 | 100
Complete R1 code, address issues | Development | Raghav, Ahana, Keerthana | 10 | 12 | Done |  | -2 | 16.6667
Revise Requirements | Requirements | Ahana | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Raghav | 0.5 | 0.75 | Done |  | -0.25 | 33.3333
Week 11 (24th March - 30th March)
Team Meeting | Coordination | Ananya | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Ahana | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client Meeting MoM | Documentation | Himani | 0.5 | 0.5 | Done |  | 0 | 0
Update backend algo | Development | Keerthana | 2 | 1.5 | Done |  | 0.5 | 33.3333
Update corresponding frontend, statistics | Development | Ahana, Keerthana | 2 | 1.75 | Done |  | 0.25 | 14.2857
Status Tracker | Documentation | Raghav | 0.5 | 0.25 | Done |  | 0.25 | 100
Week 12 (31st March - 6th April)
Team Meeting | Coordination | Himani | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Ananya | 1 | 0.5 | Done |  | 0.5 | 100
Client Meeting MoM | Documentation | Ananya | 1 | 1 | Done |  | 0 | 0
Update timetable ui, algo | Development | Ahana, Keerthana | 6 | 5 | Done |  | 1 | 20
Implement seating | Development | Raghav | 6 | 4.5 | Done |  | 1.5 | 33.3333
Status Tracker | Documentation | Raghav | 0.5 | 0.5 | Done |  | 0 | 0
Week 13 (7th April - 13th April)
Team Meeting | Coordination | Ahana | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client Meeting | Coordination | Keerthana | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client Meeting MoM | Documentation | Himani | 1 | 1 | Done |  | 0 | 0
Seating arrangement complete | Development | Raghav | 4 | 5 | Done |  | -1 | 20
Invigilation complete | Development | Ananya, Himani | 6 | 7.5 | Done |  | -1.5 | 20
Automating emails | Development | Ahana, Keerthana | 4 | 3 | Done
Status Tracker | Documentation | Raghav | 0.5 | 0.5 | Done |  | 0 | 0
Week 14 (14th April - 20th April)
Team Meeting | Coordination | Ananya | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Keerthana | 0.75 | 0.5 | Done |  | 0.25 | 50
Client Meeting MoM | Documentation | Himani | 1 | 1 | Done |  | 0 | 0
Update docs for R2 | Documentation | Himani | 5 | 4 | Done |  | 1 | 25
R2 Presentation | Documentation | Ahana | 3 | 2.5 | Done |  | 0.5 | 20
Seating Complete | Development | Raghav | 12 | 15 | Done |  | -3 | 20
Invigilation complete | Development | Ahana, Keerthana | 12 | 16.5 | Done
Fix all frontend errors | Development | Ananya | 6 | 7 | Done
Status Tracker | Documentation | Raghav | 0.5 | 0.5 | Done |  | 0 | 0